## Calendar external
Week number | Start Date | End Date | Activity type | Activities | Comments
13 | 2026-03-23 | 2026-03-24 | Schedule | T2 Synchronised Standard day
13 | 2026-03-24 | 2026-03-24 | Special testing | Open ECONSII from 10:00 - 12:00 CET | Open ECONSII from 10:00 - 12:00 CET - as replacement from regular opening on Wednesday (cancelled due to T2S ORT)
13 | 2026-03-24 | 2026-03-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period) | moved from the 25/03 because of the T2S ORT
13 | 2026-03-25 | 2026-03-25 | ORT | T2S ORT: Open during RTGS closing Day (EUR) | Impact on T2 UTEST: T2 closing day (EUR)
13 | 2026-03-25 | 2026-03-25 | Schedule | T2 closing day for EUR settlement; Standard day for DKK settlement | Due to T2S ORT: T2S open during RTGS closind day
13 | 2026-03-26 | 2026-03-26 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
13 | 2026-03-26 | 2026-03-26 | Schedule | T2 Synchronised Release day
13 | 2026-03-27 | 2026-03-27 | Schedule | T2 Closing Day
13 | 2026-03-27 | 2026-03-27 | Release deployment | T2 R2026.JUN deployment to Pre-Production (Packages 1-8) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
14 | 2026-03-30 | 2026-03-30 | Release testing | Start of testing of T2 R2026.JUN scope elements in Pre-Production
14 | 2026-03-30 | 2026-04-01 | Schedule | T2 Synchronised Standard day
14 | 2026-03-30 | 2026-04-03 | Release testing | T2 R2026.JUN release testing in Pre-Production
14 | 2026-04-01 | 2026-04-01 | Special testing | Open ECONSII from 10:00 - 12:00 CET
14 | 2026-04-01 | 2026-04-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
14 | 2026-04-02 | 2026-04-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
14 | 2026-04-02 | 2026-04-02 | Schedule | T2 closing day for DKK settlement; T2 Synchronised Standard Day for EUR Settlement | Maundy Thursday for DKK.
14 | 2026-04-03 | 2026-04-03 | Schedule | T2 closing day
15 | 2026-04-06 | 2026-04-06 | Schedule | T2 closing day
15 | 2026-04-06 | 2026-04-10 | Release testing | T2 R2026.JUN release testing in Pre-Production
15 | 2026-04-07 | 2026-04-07 | Special testing | BILL invoice for NCBs | Billing period 16-31 March
15 | 2026-04-07 | 2026-04-09 | Schedule | T2 Synchronised Standard day
15 | 2026-04-08 | 2026-04-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
15 | 2026-04-08 | 2026-04-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
15 | 2026-04-09 | 2026-04-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
15 | 2026-04-10 | 2026-04-10 | Schedule | T2 Synchronised Release day
16 | 2026-04-13 | 2026-04-15 | Schedule | T2 Live Timing | Requested by ECMS NCBs for the R2026.JUN release testing
16 | 2026-04-13 | 2026-04-17 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-15 | 2026-04-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
16 | 2026-04-15 | 2026-04-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
16 | 2026-04-16 | 2026-04-16 | Schedule | T2 Synchronised Standard day
16 | 2026-04-16 | 2026-04-16 | ORT | T2 ORT: Delay of the General Ledger (GL) file
16 | 2026-04-16 | 2026-04-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
16 | 2026-04-17 | 2026-04-17 | Release deployment | T2 R2026.JUN deployment (Package 9) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
16 | 2026-04-17 | 2026-04-17 | Schedule | T2 Synchronised Release day
17 | 2026-04-20 | 2026-04-23 | Schedule | T2 Live Timing | Requested by ECMS NCBs for the R2026.JUN release testing
17 | 2026-04-20 | 2026-04-24 | Release testing | T2 R2026.JUN release testing in Pre-Production
17 | 2026-04-22 | 2026-04-22 | Special testing | BILL invoice for NCBs | Billing period 1-19 April
17 | 2026-04-22 | 2026-04-22 | Special testing | Open ECONSII from 09:00 - 15:00 CET | upon NBB request, for AS testing
17 | 2026-04-22 | 2026-04-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
17 | 2026-04-23 | 2026-04-23 | Schedule | T2 Closing Day (DKK) | Support the testing of PBI-237005 as part of the T2 R2026.JUN campaign
17 | 2026-04-23 | 2026-04-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
17 | 2026-04-24 | 2026-04-24 | Release deployment | T2 R2026.JUN deployment (Package 10) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
17 | 2026-04-24 | 2026-04-24 | Schedule | T2 Closing day (EUR) | Support the testing of PBI-237005 and PBI-236109 as part of the T2 R2026.JUN campaign
18 | 2026-04-27 | 2026-04-29 | Schedule | T2 Live Timing | Requested by ECMS NCBs for the R2026.JUN release testing
18 | 2026-04-27 | 2026-05-01 | Release testing | T2 R2026.JUN release testing in Pre-Production
18 | 2026-04-29 | 2026-04-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
18 | 2026-04-29 | 2026-04-29 | Special testing | Open ECONSII from 09:00 - 14:00 CET | Agreed by 4CB
18 | 2026-04-30 | 2026-04-30 | Release deployment | T2 R2026.JUN deployment (Package 11) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | 2026-04-30 | 2026-04-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
18 | 2026-04-30 | 2026-04-30 | Schedule | T2 Synchronised Release day
18 | 2026-05-01 | 2026-05-01 | Schedule | T2 closing day
19 | 2026-05-04 | 2026-05-07 | Schedule | T2 Synchronised Standard day
19 | 2026-05-04 | 2026-05-08 | Release testing | T2 R2026.JUN release testing in Pre-Production
19 | 2026-05-06 | 2026-05-06 | Special testing | BILL invoice for NCBs | Billing period 20-30 April
19 | 2026-05-06 | 2026-05-06 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
19 | 2026-05-06 | 2026-05-06 | Special testing | Open ECONSII from 10:00 - 12:00 CET
19 | 2026-05-07 | 2026-05-07 | Release deployment | T2 R2026.JUN deployment (Package 12) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 2026-05-07 | 2026-05-07 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
19 | 2026-05-08 | 2026-05-08 | Schedule | T2 Synchronised Release day
20 | 2026-05-11 | 2026-05-13 | Schedule | T2 Synchronised Standard day
20 | 2026-05-11 | 2026-05-15 | Release testing | T2 R2026.JUN release testing in Pre-Production
20 | 2026-05-13 | 2026-05-13 | Release deployment | T2 R2026.JUN deployment (Package 13) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
20 | 2026-05-13 | 2026-05-13 | Special testing | Open ECONSII from 10:00 - 12:00 CET
20 | 2026-05-13 | 2026-05-13 | ORT | T2S ORT: Delay in RTGS start (processing with limited liquidity) (EUR) | Impact on T2 UTEST: T2 EUR CESO/RESO events will be rescheduled to a later point in time to simulate the RTGS delay
20 | 2026-05-13 | 2026-05-13 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
20 | 2026-05-14 | 2026-05-14 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
20 | 2026-05-14 | 2026-05-14 | Schedule | T2 closing day for DKK settlement; Synchronised Standard day for EUR settlement | DKK bank holiday: Ascension day
20 | 2026-05-15 | 2026-05-15 | Schedule | T2 closing day for DKK settlement; Synchronised Release day for EUR settlement | DKK public holiday
21 | 2026-05-18 | 2026-05-20 | Schedule | T2 Synchronised Standard day
21 | 2026-05-18 | 2026-05-22 | Release testing | T2 R2026.JUN release testing in Pre-Production
21 | 2026-05-20 | 2026-05-20 | Special testing | BILL invoice for NCBs | Billing period 1-17 May
21 | 2026-05-20 | 2026-05-20 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
21 | 2026-05-20 | 2026-05-20 | Special testing | Open ECONSII from 10:00 - 12:00 CET
21 | 2026-05-21 | 2026-05-21 | Schedule | T2 Live Timing | to support BDF's AS testing (STET).
21 | 2026-05-21 | 2026-05-21 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
21 | 2026-05-22 | 2026-05-22 | Release deployment | T2 R2026.JUN deployment (Package 14) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 2026-05-22 | 2026-05-22 | Schedule | T2 Synchronised Release day
22 | 2026-05-25 | 2026-05-25 | Schedule | T2 closing day for DKK settlement; Synchronised Standard day for EUR settlement | DKK public holiday: Whit Monday
22 | 2026-05-25 | 2026-05-27 | Release testing | T2 R2026.JUN release testing in Pre-Production
22 | 2026-05-26 | 2026-05-28 | Schedule | T2 Synchronised Standard day
22 | 2026-05-27 | 2026-05-27 | Special testing | Open ECONSII from 10:00 - 12:00 CET
22 | 2026-05-27 | 2026-05-27 | Release testing | End of testing of T2 R2026.JUN scope elements in Pre-Production
22 | 2026-05-27 | 2026-05-27 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
22 | 2026-05-28 | 2026-05-28 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
22 | 2026-05-29 | 2026-05-29 | Release deployment | T2 R2026.JUN deployment (Package 15) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
22 | 2026-05-29 | 2026-05-29 | Schedule | T2 Synchronised Release day
23 | 2026-06-01 | 2026-06-04 | Schedule | T2 Synchronised Standard day
23 | 2026-06-03 | 2026-06-03 | Special testing | BILL invoice for NCBs | Billing period 18-31 May
23 | 2026-06-03 | 2026-06-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
23 | 2026-06-03 | 2026-06-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
23 | 2026-06-04 | 2026-06-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
23 | 2026-06-05 | 2026-06-05 | Release deployment | T2 R2026.JUN deployment (Package 16) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | 2026-06-05 | 2026-06-05 | Schedule | T2 closing day for DKK settlement; Synchronised Release day for EUR settlement | DKK public day
24 | 2026-06-08 | 2026-06-11 | Schedule | T2 Synchronised Standard day
24 | 2026-06-09 | 2026-06-09 | ORT | ECMS ORT - Credit Line Misalignment | Impact on T2 UTEST: The credit line values in CLM will be updated using the ECMS cancel and replace mode.
24 | 2026-06-10 | 2026-06-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
24 | 2026-06-10 | 2026-06-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
24 | 2026-06-11 | 2026-06-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
24 | 2026-06-12 | 2026-06-12 | Schedule | T2 Synchronised Release day
25 | 2026-06-15 | 2026-06-18 | Schedule | T2 Synchronised Standard day
25 | 2026-06-17 | 2026-06-17 | Special testing | BILL invoice for NCBs | Billing period 1-14 June
25 | 2026-06-17 | 2026-06-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
25 | 2026-06-17 | 2026-06-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
25 | 2026-06-18 | 2026-06-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
25 | 2026-06-19 | 2026-06-19 | Schedule | T2 Synchronised Release day
26 | 2026-06-22 | 2026-06-25 | Schedule | T2 Synchronised Standard day
26 | 2026-06-24 | 2026-06-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
26 | 2026-06-24 | 2026-06-24 | Special testing | Open ECONSII from 10:00 - 12:00 CET
26 | 2026-06-25 | 2026-06-25 | ORT | T2 ORT: T2 Rescheduling of events (leading to delayed closing of CLM and RTGS)
26 | 2026-06-25 | 2026-06-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
26 | 2026-06-26 | 2026-06-26 | Schedule | T2 Synchronised Release day
27 | 2026-06-29 | 2026-07-02 | Schedule | T2 Synchronised Standard day
27 | 2026-07-01 | 2026-07-01 | Special testing | Open ECONSII from 10:00 - 12:00 CET
27 | 2026-07-01 | 2026-07-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
27 | 2026-07-02 | 2026-07-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
27 | 2026-07-03 | 2026-07-03 | Special testing | BILL invoice for NCBs | Billing period 15-30 June
27 | 2026-07-03 | 2026-07-03 | Schedule | T2 Synchronised Release day
28 | 2026-07-06 | 2026-07-09 | Schedule | T2 Synchronised Standard day
28 | 2026-07-08 | 2026-07-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
28 | 2026-07-08 | 2026-07-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
28 | 2026-07-09 | 2026-07-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
28 | 2026-07-10 | 2026-07-10 | Schedule | T2 Synchronised Release day
29 | 2026-07-13 | 2026-07-16 | Schedule | T2 Synchronised Standard day
29 | 2026-07-15 | 2026-07-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
29 | 2026-07-15 | 2026-07-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
29 | 2026-07-16 | 2026-07-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
29 | 2026-07-17 | 2026-07-17 | Schedule | T2 Synchronised Release day
30 | 2026-07-20 | 2026-07-23 | Schedule | T2 Synchronised Standard day
30 | 2026-07-22 | 2026-07-22 | Special testing | BILL invoice for NCBs | Billing period 1-19 July
30 | 2026-07-22 | 2026-07-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
30 | 2026-07-22 | 2026-07-22 | Special testing | Open ECONSII from 10:00 - 12:00 CET
30 | 2026-07-23 | 2026-07-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
30 | 2026-07-24 | 2026-07-24 | Schedule | T2 Synchronised Release day
31 | 2026-07-27 | 2026-07-30 | Schedule | T2 Synchronised Standard day
31 | 2026-07-29 | 2026-07-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
31 | 2026-07-29 | 2026-07-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
31 | 2026-07-30 | 2026-07-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
31 | 2026-07-31 | 2026-07-31 | Schedule | T2 Synchronised Release day
32 | 2026-08-03 | 2026-08-06 | Schedule | T2 Synchronised Standard day
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs | Billing period 20-31 July
32 | 2026-08-05 | 2026-08-05 | ORT | T2S ORT: T2S Open during RTGS closing Day (DKK) | Impact on T2 UTEST: T2 closing day in UTEST (DKK
32 | 2026-08-05 | 2026-08-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
32 | 2026-08-05 | 2026-08-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
32 | 2026-08-06 | 2026-08-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
32 | 2026-08-07 | 2026-08-07 | Schedule | T2 Synchronised Release day
33 | 2026-08-10 | 2026-08-12 | Schedule | T2 Synchronised Standard day
33 | 2026-08-12 | 2026-08-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
33 | 2026-08-12 | 2026-08-12 | Special testing | Open ECONSII from 10:00 - 12:00 CET
33 | 2026-08-13 | 2026-08-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
33 | 2026-08-13 | 2026-08-13 | Schedule | T2 Synchronised Release day | The release day is needed for the T2S R2026.SEP. The reason why no closing day on the 14/08 is because the option 2 deployment is NOT followed/required.
33 | 2026-08-14 | 2026-08-14 | Schedule | T2 Synchronised Release day
34 | 2026-08-17 | 2026-08-20 | Schedule | T2 Synchronised Standard day
34 | 2026-08-19 | 2026-08-19 | Special testing | BILL invoice for NCBs | Billing period 1-16 August
34 | 2026-08-19 | 2026-08-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
34 | 2026-08-19 | 2026-08-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
34 | 2026-08-20 | 2026-08-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
34 | 2026-08-21 | 2026-08-21 | Schedule | T2 Synchronised Release day
35 | 2026-08-24 | 2026-08-27 | Schedule | T2 Synchronised Standard day
35 | 2026-08-26 | 2026-08-26 | ORT | T2S ORT: Delay in Start of DVP cut-off (DKK) | Impact on T2 UTEST: DVP cut-off will be rescheduled to a later point in time to simulate a delay (DKK)
35 | 2026-08-26 | 2026-08-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
35 | 2026-08-26 | 2026-08-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
35 | 2026-08-27 | 2026-08-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
35 | 2026-08-28 | 2026-08-28 | Schedule | T2 Synchronised Release day
36 | 2026-08-31 | 2026-09-03 | Schedule | T2 Live Timing day
36 | 2026-09-02 | 2026-09-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
36 | 2026-09-02 | 2026-09-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs | Billing period 17-31 August
36 | 2026-09-03 | 2026-09-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
36 | 2026-09-04 | 2026-09-04 | Schedule | T2 Synchronised Release day
37 | 2026-09-07 | 2026-09-08 | ORT | T2 ORT - Activation of ECONS II - 2 days
37 | 2026-09-07 | 2026-09-10 | Schedule | T2 Live Timing day
37 | 2026-09-09 | 2026-09-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
37 | 2026-09-09 | 2026-09-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
37 | 2026-09-10 | 2026-09-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
37 | 2026-09-11 | 2026-09-11 | Schedule | T2 Synchronised Release day
38 | 2026-09-14 | 2026-09-17 | Schedule | T2 Synchronised Standard day
38 | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs | Billing period 1-13 September
38 | 2026-09-16 | 2026-09-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
38 | 2026-09-16 | 2026-09-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
38 | 2026-09-17 | 2026-09-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
38 | 2026-09-18 | 2026-09-18 | Schedule | T2 Synchronised Release day
39 | 2026-09-21 | 2026-09-22 | Schedule | T2 Synchronised Standard day
39 | 2026-09-23 | 2026-09-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
39 | 2026-09-23 | 2026-09-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
39 | 2026-09-23 | 2026-09-23 | Schedule | T2 Ad-hoc schedule due to deployment strategy
39 | 2026-09-24 | 2026-09-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
39 | 2026-09-24 | 2026-09-24 | Schedule | T2 closing day
39 | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6)
39 | 2026-09-25 | 2026-09-25 | Schedule | T2 Synchronised Release day
40 | 2026-09-28 | 2026-10-01 | Schedule | T2 Synchronised Standard day
40 | 2026-09-30 | 2026-09-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
40 | 2026-09-30 | 2026-09-30 | Special testing | Open ECONSII from 10:00 - 12:00 CET
40 | 2026-10-01 | 2026-10-01 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
40 | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | RD only
40 | 2026-10-02 | 2026-10-02 | Schedule | T2 Synchronised Release day
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs | Billing period 13-30 September
41 | 2026-10-05 | 2026-10-08 | Schedule | T2 Synchronised Standard day
41 | 2026-10-07 | 2026-10-07 | ORT | T2S ORT: Delay in RTGS start (processing with limited liquidity) (DKK) | Impact on T2 UTEST: T2 DKK CESO/RESO events will be rescheduled to a later point in time to simulate the RTGS delay
41 | 2026-10-07 | 2026-10-07 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
41 | 2026-10-07 | 2026-10-07 | Special testing | Open ECONSII from 10:00 - 12:00 CET
41 | 2026-10-08 | 2026-10-08 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
41 | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | RD only
41 | 2026-10-09 | 2026-10-09 | Schedule | T2 Synchronised Release day
42 | 2026-10-12 | 2026-10-14 | Schedule | T2 Synchronised Standard day
42 | 2026-10-14 | 2026-10-14 | ORT | T2 ORT: T2 Suspension of a participant
42 | 2026-10-14 | 2026-10-14 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
42 | 2026-10-14 | 2026-10-14 | Special testing | Open ECONSII from 10:00 - 12:00 CET
42 | 2026-10-15 | 2026-10-15 | Schedule | T2 Live Timing | support BDF's AS test (STET)
42 | 2026-10-15 | 2026-10-15 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
42 | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | critical RD only
42 | 2026-10-16 | 2026-10-16 | Schedule | T2 Synchronised Release day
43 | 2026-10-19 | 2026-10-22 | Schedule | T2 Synchronised Standard day
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs | Billing period 1-18 October
43 | 2026-10-21 | 2026-10-21 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
43 | 2026-10-21 | 2026-10-21 | Special testing | Open ECONSII from 10:00 - 12:00 CET
43 | 2026-10-22 | 2026-10-22 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
43 | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | critical RD only
43 | 2026-10-23 | 2026-10-23 | Schedule | T2 Synchronised Release day
44 | 2026-10-26 | 2026-10-29 | Schedule | T2 Synchronised Standard day
44 | 2026-10-28 | 2026-10-28 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
44 | 2026-10-28 | 2026-10-28 | Special testing | Open ECONSII from 10:00 - 12:00 CET
44 | 2026-10-29 | 2026-10-29 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
44 | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | critical RD only
44 | 2026-10-30 | 2026-10-30 | Schedule | T2 Synchronised Release day
45 | 2026-11-02 | 2026-11-05 | Schedule | T2 Synchronised Standard day
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs | Billing period 19-31 October
45 | 2026-11-04 | 2026-11-04 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | 2026-11-04 | 2026-11-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | 2026-11-05 | 2026-11-05 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only
45 | 2026-11-06 | 2026-11-06 | Schedule | T2 Synchronised Release day
46 | 2026-11-09 | 2026-11-12 | Schedule | T2 Synchronised Standard day
46 | 2026-11-11 | 2026-11-11 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2026-11-11 | 2026-11-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
46 | 2026-11-12 | 2026-11-12 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2026-11-13 | 2026-11-13 | Schedule | T2 Synchronised Release day
47 | 2026-11-16 | 2026-11-19 | Schedule | T2 Synchronised Standard day
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs | Billing period 1-15 November
47 | 2026-11-18 | 2026-11-18 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2026-11-18 | 2026-11-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2026-11-19 | 2026-11-19 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2026-11-20 | 2026-11-20 | Schedule | T2 Synchronised Release day
48 | 2026-11-23 | 2026-11-26 | Schedule | T2 Synchronised Standard day
48 | 2026-11-25 | 2026-11-25 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2026-11-25 | 2026-11-25 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | 2026-11-26 | 2026-11-26 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2026-11-27 | 2026-11-27 | Schedule | T2 Synchronised Release day
49 | 2026-11-30 | 2026-12-03 | Schedule | T2 Synchronised Standard day
49 | 2026-12-02 | 2026-12-02 | ORT | T2S ORT: RAD Tests (Inter regional failover with loss of data) | Impact on T2 UTEST: T2 EoD and SoD events will be rescheduled to an earlier point in time
49 | 2026-12-02 | 2026-12-02 | ORT | ECMS ORT: Restart After Disaster (RAD) test, covering the inter-regional failover with loss of data scenario. | Impact on T2 UTEST: ECMS unavailability due to inter-regional failover. A2A channels are closed, and messages are queued for later processing.
49 | 2026-12-02 | 2026-12-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2026-12-02 | 2026-12-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs | Billing period 16-30 November
49 | 2026-12-03 | 2026-12-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2026-12-04 | 2026-12-04 | Schedule | T2 Synchronised Release day
50 | 2026-12-07 | 2026-12-10 | Schedule | T2 Synchronised Standard day
50 | 2026-12-09 | 2026-12-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2026-12-09 | 2026-12-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2026-12-10 | 2026-12-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2026-12-11 | 2026-12-11 | Schedule | T2 Synchronised Release day
51 | 2026-12-14 | 2026-12-17 | Schedule | T2 Synchronised Standard day
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs | Billing period 1-13 December
51 | 2026-12-16 | 2026-12-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2026-12-16 | 2026-12-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2026-12-17 | 2026-12-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2026-12-18 | 2026-12-18 | Schedule | T2 Synchronised Release day
52 | 2026-12-21 | 2026-12-23 | Schedule | T2 Synchronised Standard day
52 | 2026-12-23 | 2026-12-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
52 | 2026-12-23 | 2026-12-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
52 | 2026-12-24 | 2026-12-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
52 | 2026-12-24 | 2026-12-24 | Schedule | T2 closing day
52 | 2026-12-25 | 2026-12-25 | Schedule | T2 closing day
1 | 2026-12-28 | 2026-12-30 | Schedule | T2 Synchronised Standard day
1 | 2026-12-30 | 2026-12-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
1 | 2026-12-31 | 2026-12-31 | Schedule | T2 closing day
1 | 2026-12-31 | 2026-12-31 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2027-01-01 | 2027-01-01 | Schedule | T2 closing day
2 | 2027-01-04 | 2027-01-07 | Schedule | T2 Synchronised Standard Day
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs | Billing period 14-31 December
2 | 2027-01-08 | 2027-01-08 | Schedule | T2 Synchronised Release Day
3 | 2027-01-11 | 2027-01-14 | Schedule | T2 Synchronised Standard Day
3 | 2027-01-15 | 2027-01-15 | Schedule | T2 Synchronised Release Day
4 | 2027-01-18 | 2027-01-21 | Schedule | T2 Synchronised Standard Day
4 | 2027-01-22 | 2027-01-22 | Schedule | T2 Synchronised Release Day
5 | 2027-01-25 | 2027-01-28 | Schedule | T2 Synchronised Standard Day
5 | 2027-01-29 | 2027-01-29 | Schedule | T2 Synchronised Release Day
6 | 2027-02-01 | 2027-02-04 | Schedule | T2 Synchronised Standard Day
6 | 2027-02-05 | 2027-02-05 | Schedule | T2 Synchronised Release Day
7 | 2027-02-08 | 2027-02-11 | Schedule | T2 Synchronised Standard Day
7 | 2027-02-12 | 2027-02-12 | Schedule | T2 Synchronised Release Day
8 | 2027-02-15 | 2027-02-18 | Schedule | T2 Synchronised Standard Day
8 | 2027-02-19 | 2027-02-19 | Schedule | T2 Synchronised Release Day
9 | 2027-02-22 | 2027-02-25 | Schedule | T2 Synchronised Standard Day
9 | 2027-02-26 | 2027-02-26 | Schedule | T2 Synchronised Release Day
10 | 2027-03-01 | 2027-03-04 | Schedule | T2 Synchronised Standard Day
10 | 2027-03-05 | 2027-03-05 | Schedule | T2 Synchronised Release Day
11 | 2027-03-08 | 2027-03-11 | Schedule | T2 Synchronised Standard Day
11 | 2027-03-12 | 2027-03-12 | Schedule | T2 Synchronised Release Day
12 | 2027-03-15 | 2027-03-18 | Schedule | T2 Synchronised Standard Day
12 | 2027-03-19 | 2027-03-19 | Schedule | T2 Synchronised Release Day
13 | 2027-03-22 | 2027-03-24 | Schedule | T2 Synchronised Standard Day
13 | 2027-03-25 | 2027-03-25 | Schedule | T2 closing day for DKK settlement; T2 Synchronised Standard Day for EUR Settlement | Maundy Thursday for DKK
13 | 2027-03-26 | 2027-03-26 | Schedule | T2 Closing Day | Good Friday
14 | 2027-03-29 | 2027-03-29 | Schedule | T2 Closing Day | Easter Monday
14 | 2027-03-30 | 2027-04-01 | Schedule | T2 Synchronised Standard Day
14 | 2027-04-02 | 2027-04-02 | Schedule | T2 Synchronised Release Day
15 | 2027-04-05 | 2027-04-08 | Schedule | T2 Synchronised Standard Day
15 | 2027-04-09 | 2027-04-09 | Schedule | T2 Synchronised Release Day
16 | 2027-04-12 | 2027-04-15 | Schedule | T2 Synchronised Standard Day
16 | 2027-04-16 | 2027-04-16 | Schedule | T2 Synchronised Release Day
17 | 2027-04-19 | 2027-04-22 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
17 | 2027-04-23 | 2027-04-23 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
18 | 2027-04-26 | 2027-04-29 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
18 | 2027-04-30 | 2027-04-30 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
19 | 2027-05-03 | 2027-05-05 | Schedule | T2 Synchronised Standard Day
19 | 2027-05-06 | 2027-05-06 | Schedule | T2 closing day for DKK settlement; Synchronised Standard day for EUR settlement | DKK public holiday : Ascension Day
19 | 2027-05-07 | 2027-05-07 | Schedule | T2 closing day for DKK settlement; Synchronised Release day for EUR settlement | DKK public holiday
20 | 2027-05-10 | 2027-05-13 | Schedule | T2 Synchronised Standard Day
20 | 2027-05-14 | 2027-05-14 | Schedule | T2 Synchronised Release Day
21 | 2027-05-17 | 2027-05-17 | Schedule | T2 closing day for DKK settlement; Live Timing day for EUR settlement | DKK public holiday: Whit Monday
21 | 2027-05-18 | 2027-05-20 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
21 | 2027-05-21 | 2027-05-21 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
22 | 2027-05-24 | 2027-05-27 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
22 | 2027-05-28 | 2027-05-28 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
23 | 2027-05-31 | 2027-06-03 | Schedule | T2 Synchronised Standard Day
23 | 2027-06-04 | 2027-06-04 | Schedule | T2 Synchronised Release Day
24 | 2027-06-07 | 2027-06-10 | Schedule | T2 Synchronised Standard Day
24 | 2027-06-11 | 2027-06-11 | Schedule | T2 Synchronised Release Day
25 | 2027-06-14 | 2027-06-17 | Schedule | T2 Synchronised Standard Day
25 | 2027-06-18 | 2027-06-18 | Schedule | T2 Synchronised Release Day
26 | 2027-06-21 | 2027-06-24 | Schedule | T2 Synchronised Standard Day
26 | 2027-06-25 | 2027-06-25 | Schedule | T2 Synchronised Release Day
27 | 2027-06-28 | 2027-07-01 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
27 | 2027-07-02 | 2027-07-02 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
28 | 2027-07-05 | 2027-07-08 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
28 | 2027-07-09 | 2027-07-09 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
29 | 2027-07-12 | 2027-07-15 | Schedule | T2 Synchronised Standard Day
29 | 2027-07-16 | 2027-07-16 | Schedule | T2 Synchronised Release Day
30 | 2027-07-19 | 2027-07-22 | Schedule | T2 Synchronised Standard Day
30 | 2027-07-23 | 2027-07-23 | Schedule | T2 Synchronised Release Day
31 | 2027-07-26 | 2027-07-29 | Schedule | T2 Synchronised Standard Day
31 | 2027-07-30 | 2027-07-30 | Schedule | T2 Synchronised Release Day
32 | 2027-08-02 | 2027-08-05 | Schedule | T2 Synchronised Standard Day
32 | 2027-08-06 | 2027-08-06 | Schedule | T2 Synchronised Release Day
33 | 2027-08-09 | 2027-08-12 | Schedule | T2 Synchronised Standard Day
33 | 2027-08-13 | 2027-08-13 | Schedule | T2 Synchronised Release Day
34 | 2027-08-16 | 2027-08-19 | Schedule | T2 Synchronised Standard Day
34 | 2027-08-20 | 2027-08-20 | Schedule | T2 Synchronised Release Day
35 | 2027-08-23 | 2027-08-26 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
35 | 2027-08-27 | 2027-08-27 | Schedule | T2 Synchronised Release Day
36 | 2027-08-30 | 2027-09-02 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
36 | 2027-09-03 | 2027-09-03 | Schedule | T2 Synchronised Release Day
37 | 2027-09-06 | 2027-09-09 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
37 | 2027-09-10 | 2027-09-10 | Schedule | T2 Synchronised Release Day
38 | 2027-09-13 | 2027-09-16 | Schedule | T2 Synchronised Standard Day
38 | 2027-09-17 | 2027-09-17 | Schedule | T2 Synchronised Release Day
39 | 2027-09-20 | 2027-09-23 | Schedule | T2 Synchronised Standard Day
39 | 2027-09-24 | 2027-09-24 | Schedule | T2 Synchronised Release Day
40 | 2027-09-27 | 2027-09-30 | Schedule | T2 Synchronised Standard Day
40 | 2027-10-01 | 2027-10-01 | Schedule | T2 Synchronised Release Day
41 | 2027-10-04 | 2027-10-07 | Schedule | T2 Synchronised Standard Day
41 | 2027-10-08 | 2027-10-08 | Schedule | T2 Synchronised Release Day
42 | 2027-10-11 | 2027-10-14 | Schedule | T2 Synchronised Standard Day
42 | 2027-10-15 | 2027-10-15 | Schedule | T2 Synchronised Release Day
43 | 2027-10-18 | 2027-10-21 | Schedule | T2 Synchronised Standard Day
43 | 2027-10-22 | 2027-10-22 | Schedule | T2 Synchronised Release Day
44 | 2027-10-25 | 2027-10-28 | Schedule | T2 Synchronised Standard Day
44 | 2027-10-29 | 2027-10-29 | Schedule | T2 Synchronised Release Day
45 | 2027-11-01 | 2027-11-04 | Schedule | T2 Synchronised Standard Day
45 | 2027-11-05 | 2027-11-05 | Schedule | T2 Synchronised Release Day
46 | 2027-11-08 | 2027-11-11 | Schedule | T2 Synchronised Standard Day
46 | 2027-11-12 | 2027-11-12 | Schedule | T2 Synchronised Release Day
47 | 2027-11-15 | 2027-11-18 | Schedule | T2 Synchronised Standard Day
47 | 2027-11-19 | 2027-11-19 | Schedule | T2 Synchronised Release Day
48 | 2027-11-22 | 2027-11-25 | Schedule | T2 Synchronised Standard Day
48 | 2027-11-26 | 2027-11-26 | Schedule | T2 Synchronised Release Day
49 | 2027-11-29 | 2027-12-02 | Schedule | T2 Synchronised Standard Day
49 | 2027-12-03 | 2027-12-03 | Schedule | T2 Synchronised Release Day
50 | 2027-12-06 | 2027-12-09 | Schedule | T2 Synchronised Standard Day
50 | 2027-12-10 | 2027-12-10 | Schedule | T2 Synchronised Release Day
51 | 2027-12-13 | 2027-12-16 | Schedule | T2 Synchronised Standard Day
51 | 2027-12-17 | 2027-12-17 | Schedule | T2 Synchronised Release Day
52 | 2027-12-20 | 2027-12-23 | Schedule | T2 Synchronised Standard Day
52 | 2027-12-24 | 2027-12-24 | Schedule | T2 Closing Day | Christmas
1 | 2027-12-27 | 2027-12-30 | Schedule | T2 Synchronised Standard Day
1 | 2027-12-31 | 2027-12-31 | Schedule | T2 Closing Day | Christmas